## Main
Project log
Students | Nick Glas, Ruben Stoop, Jaimy Monsuur
Student numbers | 670516, 670240, 668040
Project | ShootSoft
Team | Team Bat
Project start | 2023-02-16

## Log Nick Glas
Term 3
Week number | Start date | End date | activities | Notes
Week 1 | 2023-02-06 | 2023-02-12 | On the 6th of February, our project officially kicked off as we formed groups and began working on our assignment. We had our first cinsult with Micha and Annemarie, who gave us the project description since our client Thijs Otter was unable to attend due to illness. We worked together as a team to create the initial project documents. | Our client Thijs was unable to attend because he was sick
Week 2 | 2023-02-13 | 2023-02-19 | During our meeting with the consultants, they expressed concern that we had not done enough work on the project. This was due to the fact that the initial meeting with the client had been postponed, which delayed our progress. However, we tried our best to do as much work as possible in the meantime. The consultants suggested that we do some more research to make up for lost time. In response, I took the lead and created a research document, specifically focusing on computer vision techniques. I delved into all the techniques we had learned during our computer vision lectures and conducted research on each of them. This not only helped us make up for lost time but also taught me valuable techniques that we could use in our project.
Week 3 | 2023-02-20 | 2023-02-26 | During week 3, I watched some YouTube videos to learn about tools like Tensorflow, Keras, Tensorboard, and neural networks. Even though they were hard, these videos were really helpful because they taught me how to use these tools better. Since I didn't have any experience, it was tough to keep up with some of the videos that took seven hours to finish. But the best thing I learned from these videos was that there are computer models that can detect objects, and they use something called convolutional neural networks. I told my group about this in our next class, and we decided to check out some other tools to help us use these models for our project. We planned a new appointment at the shooting range so that we could collect more data.
Week 4 | 2023-02-27 | 2023-03-05 | As we progressed with the project, we realized that we needed a lot more data to train the model effectively. This data had to be gathered from the shooting range, but unfortunately, our client was still unable to attend the consultancy meetings and provide us with new shooting cards. However, I didn't want to wait, so I took the initiative and developed a small tool in Python that could augment the existing images in several ways. These modified images could be used to train our model. In addition to this, Jaimy found a new library that could detect bullet holes, which was a significant breakthrough for our project.
Week 5 | 2023-03-06 | 2023-03-12 | Jaimy and I worked together to annotate the images for our project. We used different tools. Jaimy used Roboflow, while I used local Python software. However, we decided to use Roboflow as an online tool that allowed us to work as a team. We uploaded all the images and began annotating them. Jaimy also tried the Roboflow tutorial and created some Python scripts, but they could only run on his computer. So, I developed a new Python script that could work on all our PCs. This script had a menu that loaded the latest dataset from Roboflow and a training menu that allowed us to train the model using our CPU or GPU. Testing the model was also possible, and I used Jaimy's script to detect the target and bullet holes in an image. All detected bullet holes were put into their own class, which helped us calculate the final score. We met with our client and showed him our progress so far. He was pleased and congratulated us on the good work.
Week 6 | 2023-03-13 | 2023-03-19 | During the sixth week, we had an important meeting with our client at the shooting range. Thijs, the client, showed us how everything worked and we had the opportunity to shoot at the targets ourselves. We used different guns, but all of them had a caliber of .22. Jaimy used a carbine rifle. We collected new shooting cards and annotated them using Roboflow. After the annotation process, I started working on setting up the API in Python since our current model detection also works in Python. I downloaded the base version of Flask provided by Wiley, but unfortunately, it did not work properly. Although I managed to get it working during the week, it was still unstable. Additionally, I created an installer that installs all the required files and packages, including the virtual environment, and also performs automatic database operations such as creating the database if needed.
Week 7 | 2023-03-20 | 2023-03-26 | During the seventh week, I continued working on the basic API. I removed some files that were causing issues for other members of the project. Ruben encountered some problems installing certain dependencies, so I decided to create an installer to simplify the process. The installer installs all necessary files and packages, including the virtual environment. I also fixed a bug in the Windows version of Flask. Additionally, the installer automates database operations, such as creating a database if needed. As always, I made sure to update the logs and other relevant documents.
Week 8 | 2023-03-27 | 2023-04-02 | In our final week, we prepared the necessary documents for the next term. Ruben worked on the graphical design, while Jaimy and I collaborated on creating the other documents. My focus was on designing the API routes and database objects.
Term 4
Week number | Start date | End date | activities | Notes
Week 9 | 2023-02-06 | 2023-02-12
Week 10 | 2023-02-13 | 2023-02-19
Week 11 | 2023-02-20 | 2023-02-26
Week 12 | 2023-02-27 | 2023-03-05
Week 13 | 2023-03-06 | 2023-03-12
Week 14 | 2023-03-13 | 2023-03-19
Week 15 | 2023-03-20 | 2023-03-26
Week 16 | 2023-03-27 | 2023-04-02

## Log Ruben Stoop
My log is in a google docs file for the convinience of using images

## Log Jaimy Monsuur
Term 3
Week number | Start date | End date | activities | Notes
Week 1 | 2023-02-06 | 2023-02-12 | Our project officially commenced on February 6th when we formed groups and started working on our assignment. During our first consultation with Micha and Annemarie, we were provided with the project description as our client, Thijs Otter, was unable to attend due to illness. As a team, we collaborated to produce the initial project documents | Our client Thijs was unable to attend because he was sick
Week 2 | 2023-02-13 | 2023-02-19 | During our meeting with the consultants, they expressed concern that we had not done enough work on the project. This was due to the fact that the initial meeting with the client had been postponed, which delayed our progress. However, we tried our best to do as much work as possible in the meantime. The consultants suggested that we do some more research to make up for lost time. In response, I took the lead and created a research document, specifically focusing on computer vision techniques. I delved in de open cv library in python, to try and find out if this could be usefull during our project. i was able te detect bulletholes and the target but not consistently. After that i desided to do some research on tensorfolow and keras and tried to make some basic models that could help us. but with our limited knollage on the subject i dot not get far.
Week 3 | 2023-02-20 | 2023-02-26 | In this week i started doing resrerch on existing convolutional neural network models , i descovered a model can yolo. i spent a few ours reeding trhough examples an documentation and then tried to make a model using yolov5. However it worked only partialy, after that i found out that there was e newer version called yolo v8, this version seemed a but easyer to get into so i desided to shift my attention to that insted. I started to annotate the images that we had reseved from thijs in a microsoft tool VOC, but soom foun out that it did not work that great, so i switched to robo flow where i annotated the 50 images. I then wrote train, validate and predidict scripts for yolov8 in python. |  | annotaties | yolov8 model
Week 4 | 2023-02-27 | 2023-03-05 | In this week i finalised the train and predict script and trained a model on my cpu. We had a meeting with the consultant this week, we showed the yolov8 model, and we got al lot of positive feedback. i continued my research on yolo. we also cocluded that we would need more data to improve the model ferther. i also desided to look into cuda, becouse the first version of the model was trained using a cpu only and i wanted to train the model on my gpu. this took a lot of time and i was not succesfull. after that i decided to look at data creation and agumentation just as nick and ruben did. |  | Roboflow
Week 5 | 2023-03-06 | 2023-03-12 | This week i explained the model and roboflow to the team. nick made a comandline python script based on my scripts from the week before, this made it easyer to train and predict images, he also changed the code so that we would not have to change the paths for every computer that we wanted to run this on, this was something that i had not doen yet. after nick was made the new tool i made some changes in my own branch an started to look at ways to use cuda in a conda env. ruben also worked on this but we still had some problem. eventualy we were able to train the model using cuda in windows however ruben and i discovered that it took alot of hours to train the model. i found it strange becouse it took almost 3 to 4 times longer to train the model on gpu then with gpu. so i desided to look into this issue.
Week 6 | 2023-03-13 | 2023-03-19 | During the sixth week, we had an important meeting with our client at the shooting range. Thijs, the client, showed us how everything worked and we had the opportunity to shoot at the targets ourselves. We used different guns, but all of them had a caliber of .22. I had the opportunity to shoot with 3 diffrent guns. We collected new shooting cards and annotated them using Roboflow. we now had a total of about 500 annotated images and with the data agumentation on roboflow the dataset was now around 1200. i then started to look at why training the model took so long, i found ongoing issues on githud regarding trainig yolov8 on windows, they explained there that there was a loop in the code responsible for loading the data, this loop apperantly di horibly on windows, but worked fine with linux, i started to look at a way to set up cude and yolo in WSL ubuntu. i changed the code so that it was now compatible with linux and i was able to set up a conda env with cuda in wsl linux. training the model now tool about 30 to 40 minutes instead of 3 and a half hour. I also started to look al other CNN model to compare them to yolo, i desided to use detectron2, i was able to get it to work on google colab linux wit cuda 10, it look about 3 hours to train, i was able to detect some bullet holes but not the targets for some reason. |  | Nieuwe annotaties | predictions | resultaten detectron
detectron2 faster rcnn
Week 7 | 2023-03-20 | 2023-03-26 | In this week i continued my work on detectron2, i wanted to get it to work with newer cude versions as it wa scurrently using cuda 10. i found out that is suported cuda 11.6 but that there was no pre compiled verson for that with torch, so the newest version thta i could set up was with cuda 11.3. i then worked on getting it to work on my machine is wsl, as yolo performed better on my machien than in google colab, a lot of hours later and that also finaly worked, i then trained the model, i was able to detect the target with an accuracy of 95% but it had diviculties with the scores of hte bullets, i assume that this is becouse all buttelts are the same except for their possition. the performance was not that bad but yolo was definetly the better option becouse it was more accurate and it took 1/4 of the time to train. In this week i als oannotated the images from the carbine and traineed a yolov8 model for that. this model had around 50 images, with data agumentation around 100 |  | Nieuwe annotaties | Nieuw yolo model
[5 empty] | detectron faster rcnn met cuda 11.3 | prediction van de eenaar laatste versie (nieuwste versie is getrained door ruben) | prediction van de karabijn model | matrix karabijn model
Week 8 + exam week | 2023-03-27 | 2023-04-02 | In our final week, we prepared the necessary documents for the next term. Ruben worked on the graphical design, while nick and I collaborated on creating the other documents. My focus was on the documents and the diagrams